## Backlog
Title | Description | Priority | Priority Comment
Refresh remaining sentences | Re-run refresh-sentences.mjs to backfill quiz chain fields (case/gender/number/tense/person) and translations for all sentences that still have needs_refresh=true. | 1 | Blocks data quality for all other features
Input guard rails | Character limit on sentence input + LLM pre-check that submitted text is actually a sentence in a natural language (blocks prompt injection). | 1 | Security — needed before any public access
Output validation | Validate GPT JSON response before saving to DB — reject if breakdown.words is empty, missing required fields, or word count is way off. Log and surface error to user. | 1 | Data integrity — prevents corrupt breakdowns reaching users
Fix word card translation display | Move translation to its own line in word card, make it more visible (currently easy to miss as grey italic inline with the type badge). | 2 | UX polish — affects every word card
Verify quiz chain questions end-to-end | After sentence refresh, manually test that case/gender/tense/person chain questions appear in quiz mode and that rationale text shows on answer. | 2 | Core feature validation
Add Conjunction / Adverb to BADGE_COLORS | lib/wordTypes.ts is missing badge color entries for Conjunction and Adverb word types. Add them so word cards don't fall back to grey. | 2 | Visual bug — affects any sentence using those word types
Nav bar | Slim persistent header replacing current ad-hoc nav buttons. Logo/name left, destination links centre (Sentences, Topics), auth right. Filter chips stay within Sentences view. | 2 | Needed before pilot — frames the app for new users
Supabase keep-alive cron | Add a scheduled job (Vercel cron or external) that pings Supabase every few days to prevent free-tier 7-day inactivity pause. | 2 | Ops reliability — free tier pauses after 7 days idle
Sentence volume | Author ~50 sentences across Beginner/Intermediate/Advanced/Expert difficulty levels and German/Latin/other languages. | 2 | Content critical mass for pilot
Vercel Pro + Supabase Pro upgrade | Upgrade both services before charging users. Vercel Pro removes hobby restrictions; Supabase Pro removes 500MB cap and inactivity pause. | 2 | Must do before any paid users
Buy msgramm.com domain | Purchase msgramm.com via Cloudflare Domains and configure DNS to point to Vercel deployment. | 3 | Needed before sharing with pilot users
Sentence-specific URLs | Each sentence gets a stable URL (e.g. /sentences/[id]). Requires ownership/privacy design first — add submitted_by uuid and is_public flag to sentences table. | 3 | Sharability and SEO — defer until ownership model designed
Sentence ownership & privacy | Add submitted_by uuid and is_public boolean to sentences table. Public sentences visible to all; private only to owner. Gate server-side sentence page on ownership. | 3 | Prerequisite for sentence-specific URLs and server-side rendering
Content library (Topics) | Grammar reference articles linked contextually from word cards. Authoring: Greg provides content → Claude converts to Editor.js JSON → insert script → Supabase. Body stored as Editor.js JSONB. Links by word_type, lemmas, or chain_answers. | 3 | MVP authoring flow already designed — no admin UI needed
Word order annotations | Sentence-level annotations explaining word order (verb-second rule, subordinate clause inversion). New breakdown JSONB field generated by GPT, or separate manual annotation. Display below sentence in study mode. | 3 | High priority for German learners — major pain point
Events system | Lightweight event log that fires on key user actions. React via Supabase realtime or webhook. Use cases: word_flagged → admin email, suspicious usage → account suspend. | 3 | Prerequisite for automated admin notifications
Account suspension mechanism | Admin ability to suspend a user account (set suspended=true, block auth). Needed to handle abuse, runaway API costs, or payment failures. | 3 | Risk management for pilot — pair with events system
Sentence star ratings | Users rate sentences 1-5 stars on quality and instructiveness. sentence_ratings table: user_id, sentence_id, rating, created_at. Aggregate shown on list and breakdown. Admin use: surface poorly-rated sentences. | 4 | Useful for pilot feedback; not blocking
Word misclassification feedback | Flag icon on each word card — one tap flags word+sentence for admin review. word_feedback table: user_id, sentence_id, wid, reported_type, suggested_type. Admin sees flagged words, can trigger refresh. | 4 | Useful quality signal; not needed at pilot launch
Parallel translation view | View mode for sentences with translations via original_id. Reference sentence at top; rows for each translation with language name and twisty to expand full breakdown. Entry: 'See in other languages' toggle. | 4 | Niche but compelling for multilingual learners
Punctuation as word entries | Include grammatically significant punctuation (e.g. German comma before subordinate clause) as word entries. GPT decides at analysis time. Word type: Punctuation. Study mode only — no chain questions. | 4 | Nice-to-have for completeness; low user demand signal yet
Knowledge tracing (ktracing) | taxonomy_nodes table (grammar hierarchy), learner_events table (logs answers against taxonomy nodes). Enables adaptive evaluation (IRT). Shares taxonomy with content library. | 5 | Long-term differentiator — design phase only